## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Preperation | 1 | 2022-06-21 | Created a new project and added some basic assets. (Unity new input system, URP, Cinemachine and some basic camera movement and my own utils class)
The algorithm | 1 | 2022-06-21 | Started working on the algorithm and working on combining it with the unity Job System for even better performance
Finishing the algorithm | 2.5 | 2022-06-22 | Finished the algorithm in combination with the unity Job system. The user is now able to (US.1) Use the algorithm to create a perfect maze and can visualise the created maze by turning on the gizmos. (for visualisation, I made use of the debug lines for now). The user is also able to (US.2) Set the width and height of the maze and make the maze uneven. US.3 also mentions something about perfomance and thanks to the Unity Job System, a 250x250 maze can be created in less than 0.07 seconds.
Designing the UI | 1 | 2022-06-22 | Created a rather simple UI design with the help of a color scheme and figma.
Setting up the UI | 2 | 2022-06-23 | Eventhough having a lack of experience building user interface, tried to make a "good" looking UI and make it work properly. The right side (as shown on the figma sketch) is pretty much done, ignoring the different algorithms and shapes.
Mesh Generation | 2.5 | 2022-06-27 | The whole maze will now be visualised with use of meshes. This reduces the match amount, thus optimises the render time and FPS. Because the meshes have a vertices cap, I made use of object pooling to create and use multiple mesh objects without the cost of any performance. The mesh generation is still unoptimized and is de bottleneck in the maze generation process.
Revisiting the UI + mesh flickering bug | 1 | 2022-06-29 | Found out the UI didn't scale properly and the mesh started to flicker if the user is looking at it from certain angles. Fixed both problems.
Added gameplay | 3 | 2022-06-30 | Besides being able to generate mazes, the user is now able to play their own mazes! A player will be spawned, which the user will have to navigate towards the flag to complete their maze. While adding this feature, i found out there were some little problems while creating the maze, which needs to be revisited if development continues, but are not a problem in the short run. | x
Minor subtle user experience features | 1 | 2022-06-30 | Added some small details. The menus close when gameplay mode is entered and open when gameplay mode is exited. The player is unable to enter playmode when there is no maze generated. Button feedback and player movement. | x
Total amount of hours | 11
Figma sketch: | https://www.figma.com/file/mADta51IqBTLna8iW4PIf0/Untitled?node-id=0%3A1
Color pallete: | https://flatuicolors.com/palette/gb